## Sheet1
Defect ID | Summary | Description | Severity | Priority | Test Phase | Assigned To | Status | Root Cause
1 | App not working in Windows System | App didn't work in windows system due to missing system files like winUtils.exe | Sev1 | Highest | Unit | QA | Closed | Env/Build
2 | Insights is creating more than 10 daily and monthly records in the generated csv files | Requirement was to generate only the top 10 most pedestrians locations but the app is generating more than 10 | Sev2 | High | Unit | Dev | Open | Code
3 | Records generated in csv files are not ordered correctly | Records generated in csv files are not ordered correctly for both daily and monthly insights | Sev3 | Medium | ST | Dev | Open | Code
4 | Requirements not clear if insights needs to be for a single day or month | Requirements not clear if insights needs to be for a single day or month | Sev3 | Medium | ST | BA | Open | Req
5 | Records generated in csv files for monthly insights doesn't have the location name | Records generated in csv files for monthly insights doesn't have the sensor/location name | Sev3 | Medium | ST | Dev | Open | Code
6 | Records generated in csv files contains unwanted/meaningless data | Records generated in csv files contains unwanted/meaningless data | Sev3 | Medium | ST | Dev | Open | Code